# Bid / No-Bid Assessment

Panama social listening services

U.S. Embassy Panama | As of 11 September 2026

Bidder: GovTribe, Inc. | 19PM0726Q0031

Quotation due: 24 September 2026, 10 a.m. Panama local time [S2 p1] [S3 block8]

GovTribe’s identity is real; scenario assumptions and past performance are illustrative.

# Recommendation

No Bid. Staffing leaves a 40-hour weekly coverage gap. Only 1 of 5 required tools/platforms is available. 5 other factors remain unresolved.

What would change the recommendation: Resolve the failed and unresolved factors by 18 September 2026. A partner could help; none is committed. Confirm whether the buyer accepts partner experience.

# Decision factors

| Factor | Status | Decision impact | Citation |
| --- | --- | --- | --- |
| Staffing coverage | Fail | 50 of 90 hours/week; 40-hour gap. Updates every 20 minutes, 6 a.m.–9 p.m., Monday–Saturday. Urgent and backup coverage is uncommitted. | [S1 pp4-6] [B1] |
| Tools and data rights | Fail | 1 of 5 required tools/platforms available. Publication coverage, export rights and supplier/AI terms are unverified. | [S1 pp4-5,23-31] [B1] |
| Relevant experience | Unresolved | Three Panama years versus five requested. Confirm whether international or partner experience qualifies. | [S1 pp4,32] [B1] |
| Security evidence | Unresolved | No questionnaire or accepted alternative assessment. Confirm critical-software attestation applicability and supplier security evidence. | [S1 pp32,36-37] [S4] [B1] |
| SAM registration | Unresolved | Current registration proof is missing. Registration is required at submission. | [S2 p1] [B1] |
| Price and margin | Unresolved | Price and delivery cost are incomplete. Include unlimited topics and urgent work; test 15% margin on sales and cash needs. | [S1 pp3,5-6] [B1] |
| Submission readiness | Unresolved | Required service samples and the signed offer package are incomplete. Scope questions remain open. | [S1 pp32-33] [B1] |
| Staff qualifications | Pass | Bilingual manager; analysts with five and seven years of experience. Availability is addressed above. | [S1 pp4,32] [B1] |

Award is based on the lowest technically acceptable price. Extra features cannot offset unmet requirements. Price the full one-year service, including urgent reports and changing topics. [S1 pp2-6,36-37]

# Next actions

| Action | Due |
| --- | --- |
| Submit the source questions before the question deadline. | 14 Sep 2026, before 10 a.m. Panama local time |
| Obtain current SAM registration proof. | 16 Sep 2026 |
| Price and commit coverage for 90 hours/week, urgent reports and backup staff. | 17 Sep 2026 |
| Secure 5 qualifying tools/platforms and verify data rights; confirm experience and obtain supplier or partner quotes. | 17 Sep 2026 |
| Complete the security questionnaire or permitted alternative; confirm attestation and AI-related obligations. | 17 Sep 2026 |
| Complete the price, margin and cash-flow review; prepare samples and the full offer package. | 17 Sep 2026 |
| Reassess the recommendation using updated evidence and record the management decision. | 18 Sep 2026 |

Recorded decision: Not recorded | Date: Not recorded

# Source questions

| Question | Citation |
| --- | --- |
| Would the buyer accept fewer than five tools/platforms? The written minimum is five; covering five networks alone does not meet it. Confirm any permitted alternative in writing. | [S1 p4] |
| Can international or partner experience qualify? Reconcile the five-year Panama requirement with the permission to supply international references. | [S1 pp4,32] |
| Which security documents apply? Confirm the questionnaire labeled Attachment 1, B and A, and whether critical-software attestation applies. | [S1 pp32,36-37,42] [S4] |
| Are focus groups and polling in scope? The submission instructions mention both; the social-listening scope does not explain them. | [S1 p33] |
| Which submission time controls? The signed cover letter and SF1449 state 10 a.m. Panama local time (15:00 UTC); GovTribe indexes 14:00 UTC. | [S2 p1] [S3 block8] |

## Source register

S1  Social Listening Dashboard and Strategic Intelligence Service RFQ. 19PM0726Q0031, issued 10 September 2026. Page citations use the printed 1-42 numbering.

S2  Signed cover letter. 10 September 2026, p. 1. Question and quotation deadlines, submission format and SAM registration.

S3  SF1449 cover form. 10 September 2026. Blocks 8 and 10 identify the deadline and unrestricted acquisition.

S4  Cybersecurity supply chain risk management questionnaire. Attachment A. C-SCRM Questionnaire sheet, instructions A2 and sections 2-3. Retrieved 11 September 2026.

## Company assumptions [B1]

Experience: Seven years of regional analytics work, including three in Panama; no real contract references or committed partner are asserted.

Team and platforms: Bilingual manager; analysts with five and seven years of experience; current coverage of 50 hours/week; 1 committed tool/platform covering the five named networks.

Company policy: 15% minimum margin on sales. Capability and cost assumptions are illustrative and dated 11 September 2026; no management approval is recorded.